# Project Schedule

By: Andrew Ng - E01

Phase: Construction

Iteration: 1

Start Date: January 19, 2025

End Date: February 2, 2026

| Discipline (Core Workflow) | Use Case or Requirement | Activity or Task | Hours Estimate | Hours Actual |
| --- | --- | --- | --- | --- |
| Design | Login | Design the Database | 3 | 2 |
|  | Book Tee Time | Design the Database | 4 | 1 |
| Implementation | Login | Create the Database | 1 | 1 |
|  |  | Create the Stored Procedures | 2 | 1 |
|  |  | Create the Frontend Page | 2 | 1 |
|  |  | Connect Backend to Database | 5 | 5 |
|  |  | Connect Backend to frontend | 5 | 3 |
|  | Book Tee Time | Create the Database | 1 | 1 |
|  |  | Create Stored Procedures | 1 | 0 |
|  |  | Create the Frontend Page | 2 | 1 |
|  |  | Connecting Backend to Database | 5 | 1 |
|  |  | Connecting Backend to frontend | 5 | 0 |

Iteration: 2 (Estimate)

Start Date: February 2, 2026

End Date: February 13, 2026

| Discipline (Core Workflow) | Use Case or Requirement | Activity or Task | Hours Estimate | Hours Actual |
| --- | --- | --- | --- | --- |
| Design | Book Tee Time | Designing the Database | 3 |  |
|  | Standing Tee Time | Designing the Database | 5 |  |
| Implementation | Book Tee Time | Create the Database | 1 |  |
|  |  | Create Stored Procedures | 1 |  |
|  |  | Create the Frontend Page | 2 |  |
|  |  | Connecting Backend to Database | 5 |  |
|  |  | Connecting Backend to frontend | 5 |  |
|  | Standing Tee Time | Create the Database | 5 |  |
|  |  | Create Stored Procedures | 5 |  |
|  |  | Create the Frontend Page | 3 |  |
|  |  | Connecting Backend to Database | 10 |  |
|  |  | Connecting Backend to frontend | 10 |  |

Project plan:

Hours per day: 5

How many days per week: 4

How many weeks: 12

Phase Plan:

| Major Milestone: | Construction |
| --- | --- |
| # Of Iterations: | 3 |
| Iteration Length (Weeks): | 2 |
| Start Date: | January 19, 2026 |
| End Date: | April 22, 2026 |

Project Schedule:

| Iteration | Minor Milestone | Start date | End Date | Hours Estimate | Hours Actual |
| --- | --- | --- | --- | --- | --- |
| 1 | Login | January 19, 2026 | January 22, 2026 | 18 | 13 |
|  | Book Tee Time | January 23, 2026 | January 30, 2026 | 18 | 4 |
| 2 | Book Tee Time | February 2, 2026 | February 7, 2026 | 17 |  |
|  | Standing Tee Time | February 8, 2026 | February 18 | 38 |  |